{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":5,"n_cols":7,"rows_kept":5,"cut":false,"hidden":false,"merged":[]}
["功能名称","计划开始时间","计划结束时间","实际开始时间","实际结束时间","完成状态","备注"]
["协议解析、数据项显示、修改、回发","—","—","—","—","完成"]
["组包拆包","2019-04-09","2019/4/110","2019-04-09","2019/4/110","完成"]
["校验、计算CRC","2019-04-11","2019-04-12","2019-04-11","2019-04-12","完成"]
["改成总线通讯方式","2019-04-28","2019-04-30",null,null,"完成"]